## Project
Blue Shield of California - Project Metrics
Project Name | Start Date |  | End Date |  |  | Project Manager Name |  |  | Requirements
| 0 |  | 0 | [5 empty] | Initial |  | Added |  | Deleted |  |  |  |  | Changed
Activity | Effort (Person days) |  |  | Schedule Variance |  |  |  |  | Schedule (duration in days) |  |  | Defect Density |  |  |  |  | Defect Leakage
| Estimated | Actual | Variance (%) | Planned start date | Planned End date | Actual Start Date | Actual end Date | Variance (%) | Estimated | Actual | Variance (%) | # of Defects |  |  | Severity |  |  | Defect Density | Defects Leaked
[12 empty] | Review Defects | Testing Defects | Total Defects | High | Medium | Low
Total | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
Effort Distribution |  |  | Process Efficiency |  |  |  | % |  | Category |  |  | Defect count | [5 empty] | Category |  | Variance Reason
Activity | % |  | Requirement Review Efficiency |  |  |  | 0% |  | # of Pre-Shipment Defects |  |  | 0 | [5 empty] | DefectDensity variance Reason
Analysis & Design | #DIV/0! |  | Design Review Efficiency | [5 empty] | # of Post-Shipment Defects | [8 empty] | RSI variance Reason
Development Unit Testing | #DIV/0! |  | Code Review Efficiency | [5 empty] | # of Post-Production Defects | [8 empty] | Design Review reason
System Integration Testing | #DIV/0! |  | Test Efficiency | [5 empty] | Defect Removal Efficiency | [8 empty] | Code Review Reason
Security testing | #DIV/0! |  | Overall review efficiency |  |  |  | 0%
Performance testing | #DIV/0!
UAT Support | #DIV/0! |  | Other Metrics | [5 empty] | Defect Distribution
Warranty Support | #DIV/0! |  | Effort variance (%) |  |  |  | 0 |  | Category | %
Project mgmt. | #DIV/0! |  | Schedule Variance (%) |  |  |  | 0% |  | Reqs | 0%
|  |  | Requirements Stability Index |  |  |  | 0 |  | Design | 0%
|  |  | Defect Density by effort |  |  |  | 0 |  | Code | 0%
|  |  | Residual Defect Density |  |  |  | 0 |  | Testing | 0%
Others
Formulas:
Schedule Variance = MIN(E9:[Schedule Variance, row above])
Planned End date = MAX(F9:[Planned End date, row above])
Project Manager Name = MIN(G9:[Project Manager Name, row above])
Actual end Date = MAX(H9:[Actual end Date, row above])
Requirements = NETWORKDAYS([Schedule Variance],[Planned End date])
Actual = NETWORKDAYS([Project Manager Name],[Actual end Date])

## MetricsData (hidden)
Metrics Sheet
Project Name | Sub Project | PM ID | Project Manager |  | Start Date |  | End Date |  |  | Project type
[10 empty] | Size | UOM
Effort | Estimated |  | Actual |  | Variance | 0% |  |  |  | Estimated Size | Actual Size | % Size Variation
Requirements | Initial |  | Added |  | Deleted |  | Changed |  |  |  |  | #DIV/0!
Activity | Effort (Person days) |  |  | Schedule Variance |  |  |  |  | Schedule (duration in days) |  |  | Defects (shaded cells MUST NOT contain entries) | [9 empty] | Defect Leakage
| Estimated | Actual | Variance (%) | Planned start date | Planned End date | Actual Start Date | Actual end Date | Variance (%) | Estimated | Actual | Variance (%) |  | Deliverable |  |  |  |  | Severity |  |  | Defect Density | Defects Leaked | Total no of Defects Attributed to PD | Defect Leakage % | [8 empty] | Effort |  | Schedule
[12 empty] | Total | Reqs | Design | Code | Test Planning | Doc | High | Medium | Low | [12 empty] | Baseline | Actual | Baseline | Actual
SRS | 36 | 42 | 16.67% |  |  |  |  | #DIV/0! | 6 | 7 | 16.67% | [12 empty] | #DIV/0! | [8 empty] | #REF! | #REF! | 6 | 7
SRS Review | 12 | 18 | 50% |  |  |  |  | #DIV/0! | 2 | 3 | 50% | 38 |  |  |  |  | 38 | 0 | 11 | 27 | 2.1111 |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 8 | 10
ST Planning | 24 | 24 | 0% |  |  |  |  | #DIV/0! | 4 | 4 | 0% | [12 empty] | #DIV/0! | [8 empty] | #REF! | #REF! | 12 | 14
ST Plan Review | 6 | 11.5 | 91.67% |  |  |  |  | #DIV/0! | 1 | 1.9 | 90% | 64 |  |  |  | 6 | 58 | 6 | 9 | 49 |  |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 13 | 15.9
DD (HLD + LLD) | 36 | 66 | 83.33% |  |  |  |  | #DIV/0! | 6 | 11 | 83.33% | [12 empty] | #DIV/0! | [8 empty] | #REF! | #REF! | 19 | 26.9
DD Review | 14 | 24.5 | 75% |  |  |  |  | #DIV/0! | 2 | 3.5 | 75% | 205 |  | 113 |  |  | 92 | 46 | 67 | 92 |  |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 21 | 30.4
IT Planning | 28 | 35 | 25% |  |  |  |  | #DIV/0! | 4 | 5 | 25% | [12 empty] | #DIV/0! | [8 empty] | #REF! | #REF! | 25 | 35.4
IT Plan Review | 14 | 14 | 0% |  |  |  |  | #DIV/0! | 2 | 2 | 0% | 113 |  |  |  | 84 | 29 | 32 | 52 | 29 |  |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 27 | 37.4
Coding | 30 | 36 | 20% |  |  |  |  | #DIV/0! | 5 | 6 | 20% | [12 empty] | #DIV/0! | [8 empty] | #REF! | #REF! | 32 | 43.4
Code Review | 18 | 22 | 22.22% |  |  |  |  | #DIV/0! | 3 | 4 | 33.33% | 158 |  |  | 158 |  |  | 65 | 58 | 35 |  |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 35 | 47.4
UT Planning | 24 | 26 | 8.333% |  |  |  |  | #DIV/0! | 4 | 4.5 | 12.5% | [12 empty] | #DIV/0! | [8 empty] | #REF! | #REF! | 39 | 51.9
UT Plan Review | 12 | 12 | 0% |  |  |  |  | #DIV/0! | 2 | 2.3 | 15% | 121 |  |  |  | 121 |  | 28 | 53 | 40 |  |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 41 | 54.2
Unit test | 96 | 108 | 12.5% |  |  |  |  | #DIV/0! | 16 | 18 | 12.5% | 44 |  |  | 44 |  |  | 8 | 23 | 13 | 0.40741 |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 57 | 72.2
Integration test | 48 | 60 | 25% |  |  |  |  | #DIV/0! | 8 | 10 | 25% | 36 |  | 1 | 35 |  |  | 17 | 15 | 4 |  |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 65 | 82.2
System test | 60 | 66 | 10% |  |  |  |  | #DIV/0! | 10 | 11 | 10% | 31 |  | 4 | 27 |  |  | 3 | 25 | 3 | 0.4697 |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 75 | 93.2
Performance Testing |  |  | 0% |  |  |  |  | #DIV/0! |  |  | 0% | [9 empty] | #DIV/0! |  |  | #DIV/0!
Acceptance |  |  | 0% |  |  |  |  | #DIV/0! |  |  | 0% | 0 | [8 empty] | #DIV/0! |  |  | #DIV/0! | [8 empty] | #REF! | #REF! | 75 | 93.2
Support |  |  | 0% |  |  |  |  | #DIV/0! |  |  | 0% | 0 | [11 empty] | #DIV/0!
Project mgmt. | 53 | 65 | 22.64% |  |  |  |  | #DIV/0! |  |  | 0% | [12 empty] | #DIV/0!
QA | 2 | 2 | 0% |  |  |  |  | #DIV/0! |  |  | 0% | [9 empty] | 0 |  |  | #DIV/0!
Training - team |  |  | 0% |  |  |  |  | #DIV/0! |  |  | 0% | [12 empty] | #DIV/0!
Training - user |  |  | 0% |  |  |  |  | #DIV/0! |  |  | 0% | [12 empty] | #DIV/0!
CM | 6 | 6 | 0% |  |  |  |  | #DIV/0! |  |  | 0% | [12 empty] | #DIV/0!
Others |  |  | 0% |  |  |  |  | #DIV/0! |  |  | 0% | [12 empty] | #DIV/0!
Total | 519 | 638 | 22.93% | 0 | 0 | 0 | 0 | #DIV/0! | 75 | 93.2 | 24.27% | 810 | 0 | 118 | 264 | 211 | 217 | 205 | 313 | 292 | 1.2696 | 0 | 0 | #DIV/0!
Effort Distribution |  |  | Defect Distribution |  |  |  |  | Process Efficiency |  |  |  | % |  | Other Metrics | [11 empty] | SRS | DESIGN | CODING | TEST PLANNING | TESTING | ACCEPTANCE | SUPPORT | PROJECT MGT. | QA | TRG. | CM | OTHERS
Activity | % |  | Category | % | Severity | % |  | SRS Review Efficiency |  |  |  | 0% |  | Effort variance (%) |  | 22.93% | [8 empty] | effort | 0.25 | 0.81 | 0.20833 | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | 0.22642 | 0 | #DIV/0! | 5 | #DIV/0!
SRS | 9.404% |  | Reqs | 0% | High | 25.31% |  | Design Review Efficiency |  |  |  | 95.76% |  | Schedule Variance (%) |  | #DIV/0! | [8 empty] | Schedl | 0.25 | 0.8125 | 0.25 | #REF! | 0.14706 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Design | 14.18% |  | Design | 14.57% | Medium | 38.64% |  | Code Review Efficiency |  |  |  | 59.85% |  | Size Variance (%)(KLOC) |  | #DIV/0!
Coding | 9.091% |  | Code | 32.59% | Low | 36.05% |  | Test Efficiency |  |  |  | 100% |  | Requirements Stability Index |  | 0
Test Planning | 19.2% |  | Test Pln | 26.05% |  |  |  | Overall review efficiency |  |  |  | 86.3% |  | Defect Density by effort |  | 0
Testing | 36.68% |  | Doc | 26.79% | [9 empty] | Residual Defect Density |  | 0
Acceptance | 0% |  | Others
Support | 0%
Project mgmt. | 10.19% |  | Category | Defect count
QA | 0.3135% |  | # of Pre-Shipment Defects
Training - team | 0% |  | # of Post-Shipment Defects
Training - user | 0% |  | # of Post-Production Defects
CM | 0.9404% |  | Defect Removal Efficiency | #DIV/0!
Others | 0%
SRS review to SRS total |  |  | 30%
Test Plan review to plan total |  |  | 30.61%
Design review to design total |  |  | 27.07%
Code Review to code total |  |  | 37.93%
Overall Review Effort to total effort |  |  | 15.99%
Formulas:
Schedule Variance = MIN(E13:[Schedule Variance, row above])
Start Date = MAX(F13:[Start Date, row above])
Actual Start Date = MIN(G13:[Actual Start Date, row above])
End Date = MAX(H13:[End Date, row above])

## Metrics Analysis (hidden)
Sl No. | Metrics | Formula | Frequency | Expected Range(LSL - Goal - USL) | Service Level Metric | Source of Metrics | Data availability | Remarks
1 | Requirements Stability Index (RSI) | (No of Original requirements + No of CRs)/No of Original Requirements | Monthly | 1.00 - 1.05 - 1.18 | Project Level | Interface Dashboard XL | 0
2 | Design Review Efficiency (Tech Design) | No of Design Review Defects/(total no of review + testing defects) | Monthly | 76.84– 83.37 –85.76 | Project Level | Design Review Tracker, JIRA | 95.76%
4 | Schedule Deviation (Tech Design) | Actual end date – planned end date/(planned end date – planned start date) | Monthly | 0.0 – 1.32 - 5.18 | Work Item Level | Project Plan | #DIV/0! | Planned and actual end dates required
6 | Code Review Efficiency | No of Code Review Defects/(total no of review + testing defects) | Monthly | 92.5 – 86.65 – 81.11 | Project Level | Code review Tracker, JIRA | 59.85%
8 | Defect Leakage (Unit Testing) | Sum((Number of defects attributed to a stage but only captured in subsequent stages) / (Total number of defects captured in that stage + Total Number of defects attributed to a stage but only captured in subsequent stages)) | Monthly | 15.5 – 17.26 – 23.74 | Project Level | JIRA, Defect Tracker | #DIV/0! | 105.5849
9 | Defect Density (Unit Testing) | Total unit testing Defects/Actual Effort | Monthly | 0.06 – 0.09 – 0.29 | Project Level | JIRA, Project Plan | 0.40741 | 0.068966
11 | Defect Density (Only Performance defects identified in Performance Testing) | Total Performance Defects/Actual Effort | Monthly | 0.06 – 0.07 – 0.24 | Project Level | JIRA, Project Plan | #DIV/0!
12 | Defect Density (for each of the Testing phases - QA/SIT/UAT) | Total Defects in each phase/Actual Effort | Monthly | 0.07 – 0.10 – 0.33 | Project Level | JIRA, Project Plan |  | Can be selected based on the Testing phase
13 | Defect Leakage (for each of the Testing phases -QA/SIT/UAT) | Sum(no of defects attributed to a stage but captured in subsequent stage)/ total defects captured in that stage + no of defects attributed to a stage but captured in subsequent stage | Monthly | 15.16 – 16.00 – 28.2 | Project Level | JIRA, Defect Tracker | #DIV/0!
15 | Defect Removal Efficiency | Total Preshipment defects/ (total preshipment defects + post shipment defects + post production defects) | Monthly | 88.46 – 93.94 – 98.13 | Project Level | Defect Tracker, JIRA | #DIV/0!
10 | Code Release Defect RCA | Root Cause Analysis for each of the Code Deployment Defects | Monthly | N/A | Project Level | Defect Tracker, JIRA
14 | RCA (for each of the testing phases - QA/SIT/UAT) |  | Monthly | N/A | Project Level | Defect Tracker, JIRA
7 | Code Quality (From Platinum or SONAR tool) |  | At the Time of Delivery | N/A | Work Item Level | Tool
3 | Design Accuracy | TBD (BSC PMO to provide inputs) | Monthly | TBD | Project Level | TBD
5 | Build Accuracy | TBD (BSC PMO to provide inputs) | Monthly | TBD | Project Level | TBD