## Project Metric Information
Blue Shield of California - Project Metrics
Tower |  |  | Project Manager Name |  |  |  |  | Requirements
Portals and Mobility |  |  | Prasad Kondisetti |  |  |  |  | Initial | 80 | Deleted | 3 | Added | 7 | Changed | 0
Projects | Effort(Person days) |  |  | Schedule Variance |  |  |  |  | Schedule (duration in days) |  |  | Review Comments | [5 empty] | Defect Density
| Estimated Effott(PD) | Actual Effort(PD) | Variance (%) | Planned start date | Planned End date | Actual Start Date | Actual end Date | Variance (%) | Estimated | Actual | Variance (%) | Offshore Review |  |  | Onsite Review (includes Client review) |  |  | # of Defects |  |  |  | Total Defects | Defect Density
| Total | Total | [9 empty] | Design Review comments | UTC review Comments | Code Review Comments | Design Review comments | UTC review Comments | Code Review Comments | UT Defects | QA Reqmn Defects | QA Design Defects | QA Code Defects
Phoenix HCR | 207 | 207 | 0% | 2014-05-01 | 2014-05-31 | 2014-05-01 | 2014-05-31 | 0% | 23 | 23 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 0.048309 | 0 | 0
Portals Production Support | 39 | 39 | 0% | 2014-05-01 | 2014-05-31 | 2014-05-01 | 2014-05-31 | 0% | 23 | 23 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom_Group | 42 | 32 | -23.81% | 2014-05-01 | 2014-05-31 | 2014-05-01 | 2014-05-31 | 0% | 46 | 46 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Member HCR | 63 | 63 | 0% | 2014-05-01 | 2014-05-31 | 2014-05-01 | 2014-05-31 | 0% | 23 | 23 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.015873
Total | 351 | 341 | -0.02849 | 2014-05-01 | 2014-05-31 | 2014-05-01 | 2014-05-31 | 0% | 115 | 115 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 11 | 0.016046
| Process Efficiency |  |  | 0% |  |  |  |  | Category |  |  | Defect count
| Design Review Efficiency |  |  | 100% |  |  |  |  | # of Pre-Shipment Defects |  |  | 11
| Code Review Efficiency |  |  | 0% |  |  |  |  | # of Post-Shipment Defects |  |  | 0
[9 empty] | # of Post-Production Defects |  |  | 0
[9 empty] | Defect Removal Efficiency |  |  | 100
Other Metrics
| Schedule Variance (%) |  |  | 0%
| Requirements Stability Index |  |  | 1.125
Formulas:
Schedule Variance = MIN(E9:[Schedule Variance, row above])
Planned End date = MAX(F9:[Planned End date, row above])
Actual Start Date = MIN(G9:[Actual Start Date, row above])
Actual end Date = MAX(H9:[Actual end Date, row above])

## ReviewEfficiency
Efficiency | Calc. Metrics | Benchmark
Code Rev. Efficiency |  | 87
Defect Rem. Efficiency | 100 | 87
Desgn Rev. Efficiency | 100 | 92

## SchedVariance
Schedule Variance | Calc. Metrics | Benchmark
Schedule Variance | 0 | 3.31

## RSI
Projects | RSI | Benchmark
Phoenix HCR | 1.06 | 1.13
Portals Production Support | 1 | 1.13
Custom_Group | 1.194 | 1.13
Member HCR | 1.5 | 1.13

## DefectDensity
Projects | DefectDensity | Benchmark
Phoenix HCR | 0.048 | 0.19
Portals Production Support | 0 | 0.19
Custom_Group | 0 | 0.19
Member HCR | 0.016 | 0.19